## Project Charter
Project Name | Build Planet Zero Sensory Garden #2
Project Sponsor | Northumbria University |  | Project Manager | Kufre Antia
Approval Date |  |  | Revision Date
Project Description | Build Planet Zero Sensory Garden #2 transforms Nuns Moor Park’s Sensory Garden and Depot buildings into a Net-Zero Community Arts Centre, featuring renewable energy, sustainable materials, inclusive spaces, and biodiversity-focused landscaping.
Scope | Sensory Garden Renovation | Sustainable Material Usage | Outdoor Activity & Play Zones
| Net-Zero Energy Integration | Ecological Regeneration | Water Management & Efficiency
Constraints | Regulatory & Compliance Constraints |  | Space & Site Limitations
| Time Constraints |  | Sustainability & Material Sourcing
Deliverables | Design Document |  | BIM Execution Plan
| VR Walk through |  | Consultancy Report
Benefits | Environmental Benefits | Social & Community Benefits | Economic Benefits Educational & Awareness Benefits
KPIs | Phase 1 Kick Off | Phase 2 Mid Term | Phase 3 Final | Feedback
Steering Committee | Project Sponsor | Academic Supervisor | Project Management Consultant | Team Dynamics Lead
| Northumbria University | Ray Elysee | John Arthur | Anne Macdonald
Key Stakeholders | Northumbria University | Build Planet Zero Llimited | J Arthur Consult | BPZ #2
Risk | Planning | Data Collection | Team Dynamics | Stakeholder Mang.
| Delays | Human Resource Limitations | Skill gaps | Environmental uncertainties
| Sustainability Integration Risks | Communication Limitations | Technological Limitations | workload imbalance
Lack of Research Materials on Newcastle Ecology & Domes

## Project Team
SN | NAME | EMAIL (northumbria) | TEAM ROLES | PROJECT MANAGEMENT ROLE | PROJECT DELIVERY ROLE
|  |  | TR 1 | TR2 | TR3
|  |  | Anne Mcdonald | John Authur | Ray Elysee
1 | Kufre Usen Antia | kufre.antia@northumbria.ac.uk | Plant | Project Manager | Project Delivery Manager
2 | Jaayaprekesh |  |  | Assistant Project Manager | Design Lead
3 | Collins Tamunotonye |  |  | Document Controller | Sustainability Lead
4 | Shebi | shebi.maheswari@northumbria.ac.uk |  | Project Scheduler | Research Lead

## Roles and Responsibilities
Project Management |  |  | Project Delivery
S.No | Role | Responsibilities | S.No | Role | Responsibilities
1 | Project Manager | Reports to project consultant, EE team and academic supervisor | 1 | Project Delivery Lead | Reports to project consultant, EE team and academic supervisor
|  | Supervises project team |  |  | Supervises project team
|  | Allocates tasks in line with project schedule |  |  | Research on MMC
|  | Creates project charter |  |  | Preparation of BEP
2 | Assistant Project Manager | Reports to project manager | 2 | Design Lead | Drafting of design proposals
|  | Supports projects manager |  |  | Development of Detailed design
3 | Project Scheduller | Reports to project manager | 3 | Research Lead | Research on Ecology
|  | Updates project schedule and provides insight on project health in regards to schdule compliance |  |  | Research on Ecology
4 | Document Controler | Reports to project manager | 4 | Sustainability Lead | Research on Sustainable Material
|  | Monitors project folder and ensures proper file naming |  |  | Research on Net-Zero
Monitors changes in project scope and updates projects documents
Project Delivery
S.No | Role | Responsibilities
1 | Project Delivery Lead | Reports to project consultant, EE team and academic supervisor
Supervises project team
Research on MMC
Preparation of BEP
2 | Research Lead | Research on Ecology
Research on Ecology
3 | Design Lead | Drafting of design proposals
Development of Detailed design
4 | Sustainability Lead | Research on Sustainable Material
Research on Net-Zero

## Task
20.03.2025
| Project Management Task |  |  | Status | Project Delivery Task |  |  | Status
| Role | Task | Due Date |  | Role | Task | Due Date
| Project Manager | Conduct Risk Assessment | 21.03.2025 | Completed 24.03.2025 | Delivery Lead | Develop Communication Plan | 27.03.2025 | Completed 24.03.2025
| Assitant Project Manager | Follow up with team members to ensure task is executed on time and update the status | 21.03.2025 |  | Design Lead | Make two sketches integrating the existing building with the design as discussed | 27.03.2025 | Completed 26.03.2025
| Project Scheduler | Complete and Update project schedule, Update Project Presentation incooperating feedback | 21.03.2025 | Completed 28.03.2025 | Research Lead | Reward - Rest - Weldone on proactivity |  | Team member of the week award | TMoTW
| Document Controller | Prepare a google form using the questions from the slide. Ensure that all files are properly named | 21.03.2025 | Completed 28.03.2025 | Sustainability Lead | Research on hydrafrom interlocking blocks, including the properties of UK's Lateritic soil. | 27.03.2025
27.03.2025
| Project Management Task |  |  | Status | Project Delivery Task |  |  | Status
| Role | Task | Due Date |  | Role | Task | Due Date
| Project Manager | Create project closure plan | 31.03.2025 | Completed 29.03.2025 | Delivery Lead | Create Mindmap linking client's deliverables to proposed solution | 31.03.2025 | Completed 29.03.2025
TMoTW | Assitant Project Manager | Follow up with team members to ensure task is executed on time and update the status | 31.03.2025 | Completed 29.03.2026 | Design Lead | Make final sketch for developemnt | 01.04.2025 | Completed 01.04.2025
| Project Scheduler | Review project closure plan and update this task sheet with new task from project plan | 31.03.2025 | Completed 29.03.2027 | Research Lead | Create draft structure of final report | 04.04.2025 | Completed 01.04.2025
| Document Controller | Prepare a questionaire using the questions from the slide. Ensure that all files are properly named | 21.03.2025 | Completed 29.03.2028 | Sustainability Lead | Research on hydrafrom interlocking blocks, including the properties of UK's Lateritic soil. | 04.04.2026 | Completed 01.04.2026
03.04.2025
| Project Management Task |  |  | Status | Project Delivery Task |  |  | Status
| Role | Task | Due Date |  | Role | Task | Due Date
| Project Manager | Allocate task | 10.04.2025 | Completed | Delivery Lead | Research and report on BIM based DfMA of design. Develop integrated proposal for DfMA and renewable energy integration into preliminary design and report | Overdue | Under Elimination consideration
| Assitant Project Manager | Follow up with team members to ensure task is executed on time and update the status | 10.04.2026 | Completed | Design Lead | Develop detailed 3D design of structure at LOD 300 incoperating renewable energy and DfMA solutions. | 10.04.2026 | Completed 10.04.2025 | TMoTW
| Project Scheduler | Track project performance inline with schedule | 10.04.2027 | Completed | Research Lead | Create draft of final presentation | 10.04.2027
| Document Controller | Collect and upload all present design documents from JayP in the designated folder on teams | 10.04.2028 | Completed | Sustainability Lead | Identify optimal locations within the design for solar panels and other renewable systems. | 10.04.2028 | Completed 29.03.2028
10.04.2025
| Project Management Task |  |  | Status | Project Delivery Task |  |  | Status
| Role | Task | Due Date |  | Role | Task | Due Date
| Project Manager | PROJECT MANAGER |  |  | Delivery Lead | Develop integrated proposal for DfMA and renewable energy integration into Preliminary Design. considering energy requirement and solar panel requirement | 15.04.2025 | Under Elimination consideration
| Assitant Project Manager |  |  |  | Design Lead | Simulate impact of passive strategies on overall energy consumption. And check for compliance with PAssivehaus, using a mindmap to link design concept to requirment for passivhaus certification. Point out location that require Bricks | 15.04.2025
| Project Scheduler |  |  |  | Research Lead | Laise with JayP and generate a material quantity take off, then using that write the material selection reoprt for our final report. | 15.04.2025
| Document Controller | Get with the respective team members and collect the all project research documents and save in the right folder |  |  |  | Reseach potential suppliers and stakeholdersand their loaction and prepare a one page report for embodied carbon goals | 15.04.2025
17.04.2025
| Project Management Task |  |  | Status | Project Delivery Task |  |  | Status
| Role | Task | Due Date |  | Role | Task | Due Date
| Project Manager | PROJECT MANAGER |  |  | Delivery Lead | Work on technical report
| Assitant Project Manager |  |  |  | Design Lead | Create 3D rendered model in Lumion/Twinmotion and prepare a Passivehaus compliance report for the technical report | 18.04.2025
| Project Scheduler |  |  |  | Research Lead | Identify risks and mitiagtion associated with delivery of design | 23.04.2025
Document Controller
24.04.2025
| Project Management Task |  |  | Status | Project Delivery Task |  |  | Status
| Role | Task | Due Date |  | Role | Task | Due Date
| Project Manager | PROJECT MANAGER |  |  | Delivery Lead
| Assitant Project Manager |  |  |  | Design Lead | VR walkthrough and high-quality rendered images of final model | 23.04.2025
| Project Scheduler |  |  |  | Research Lead
Document Controller

## Communication Plan
Design of West End Community Sensory Garden and Art Centre |  |  |  | Feedback
Introduction
Item | Details
Project Overview | Design of a Net-Zero Community Arts Centre, featuring renewable energy, sustainable materials, inclusive spaces, and biodiversity-focused landscaping
Purpose | Establish clear, consistent, and open communication channels; manage stakeholder expectations; and facilitate timely decision-making.
Communication Objectives
Item | Details
Timeliness | Ensure all communications are delivered promptly to support project milestones.
Clarity | Present information in a clear, consistent, concise, and accessible format.
Consistency | Maintain a consistent message aligned with project goals and organizational values.
Engagement | Encourage feedback and active participation from stakeholders.
Transparency | Provide regular updates on project progress, risks, and decisions.
Stakeholder Identification
Stakeholder Group | Role / Interest | Influence | Information Needs
Project Team (Build Planet Zero #2) | Responsible for executing the design and ensuring quality. | High | Weekly progress updates, milestone tracking
Faculty of Built Environment (Academic Supervisor) | Provides academic guidance and oversees design quality. | Medium | Research reports, design drafts
Project Management Consultant (J Arthur Consult) | Manages project oversight and team performance. | High | Project charter document
EE Professional (Organizational Dynamics Lead) | Distribution partners and hosts | Medium | Kick-off, mid term and final Presentations
Client (Build Planet Zero Limited) | The primary decision-maker for the project outcomes. | High | Kick-off, mid term and final Presentations. Technical Report, BEP and Design documents
Project Team (Build Planet Zero #1) | Sister project team, avalable for intellectual discourse on project | Low | None
Stakeholder Analysis
Stakeholder | Power (0–1) | Interest (0–1) | Explanation
Build Planet Zero Team 2 (Design Delivery Team) | 0.9 | 0.9 | Key driver with high influence and high interest in project execution.
EE Professional (Organizational Dynamics Lead) | 0.85 | 0.9 | High influence on team dynamics and internal operations, making them a critical stakeholder.
Faculty of Built Environment (Academic Supervisor) | 0.3 | 0.8 | Highly interested in academic rigor and design quality, but with lower decision-making authority; acts in an advisory capacity.
J Arthur Consult (Project Management Consultant) | 0.4 | 0.4 | Moderately influential regarding overall project management; interest is lower on the detailed aspects of the design project.
Built Planet Zero Limited (Client) | 0.95 | 0.95 | Holds the highest power and interest, directly influencing project outcomes and overall direction.
Communication Channels and Methods
Method | Frequency | Audience | Purpose
Kick-off Meeting | Once | All Stakeholders | Alignment on goals and scope
Weekly Team Check-ins | Weekly | Project Team | Monitor progress, task allocation and feedback
Project Management Tranings | Termly (Four in total) | Project Management consultant | Recieve traning on keys aspects of project management including
Industrial Supervision | Termly (Kick-off, Midterm, Close-out | Project Management consultant | Share progress and receive feedback
Mid-Term Meeting | Once | Client | Share progress and receive feedback from Client
Final Meeting | Once | Client | Share progress and receive feedback from Client
Email Microsoft Teams | As needed | All Stakeholders | Streamlined Communication
Presentations | Feb, March & May 2025 | Client | Scope and purpose alignment, progress and feedback, performance and outcome
Final Report | March & May 2025 | Client | Project performance and outcomes
Roles and Responsibilities
Role | Responsibility
Project Manager | Oversees all communications, point of contact
Assitant Project Manager | Oversees progress of team members on task and reports to Project Manager
Project Scheduler | Ensures alignment of communicated documents with schedule
Document Controler | Ensures all communicated documents follow consitent naming and documentation format
Feedback and Evaluation Mechanisms
Item | Details
Surveys and Questionnaires | Google form for feedback on midterm presentation questions
Review Meetings | Periodic sessions to discuss feedback, adapt strategies, and address concerns.
Industrial Trainings | Trainings on critial skills and facets of project management
Industrial Supervision | Periodic assesment of project progress
Risk Management in Communication
Section/Item | Details
Mitigating Miscommunication | Use standardized templates and consistent terminology.
Addressing Delays | Develop contingency communication plans for setbacks.
Information Quality | Establish clear protocols for differentiating internal and external communications, including naming convention for files and allocating a document controler for oversight.
Handling Sensitive Information | Establishing a private MS Teams group for storing information away from PM group based on the NDA associated with the project
Approval and Sign-Off
Section/Item | Details
Review | Plan to be reviewed by the project management Consultant
Review Frequency | As needed

## Risk Assessment
Risk Assessment
Risk Category | Risk | Mitigation | Militating Measures
Sustainability Integration Risks | Difficulty in seamlessly integrating net-zero strategies, renewable energy systems, and passive design principles. | Conduct in-depth research and consult with sustainability experts during the early design phase. | • Develop alternative design solutions that balance environmental performance with aesthetic and functional goals. • Establish clear sustainability benchmarks (e.g., Passivhaus standards) as part of the design requirements.
Technological Limitations | Inadequate computing power or device failure due to reliance on personal laptops. | Use cloud-based storage and shared platforms to ensure continuity across devices. | • Request access to institutional or project-funded hardware (e.g., laptops or workstations). • Ensure regular data backups and version control to minimize disruption.
Human Resource Limitations | Potential disruption to team roles due to illness or health-related issues, especially during seasonal changes. | Designate assistant roles for each critical task to ensure continuity. | • Enable remote working options to reduce exposure and support flexibility. • Schedule check-ins to monitor workload and well-being.
Communication Limitations | Difficulty in establishing a shared mental model of the design concept across the team. | Use VR tools, shared visual aids, and schedule in-person design workshops. | • Increase the frequency of team meetings, both virtual and in person. • Maintain a shared live document outlining design intent, decisions, and rationale.
Lack of Research Materials on Newcastle Ecology & Domes | Difficulty in accessing specific ecological data and dome design precedents relevant to the Newcastle context. | Explore academic databases, local authority archives, and engage with environmental organisations. | • Reach out to local experts and community stakeholders for qualitative insights. • Use comparative case studies where direct data is unavailable, with room for design adaptation as more information becomes available.