## 04.02.2025 v1.0 (2) (hidden)
West End Community Sensory Garden
Build Planet Zero #2
KEYS
Completed
Not completed
Overdue tasks
|  |  |  | Delayed Completion |  |  |  | Week-1 |  |  |  |  | Week-2 |  |  |  | Week-3 |  |  |  |  | Week-4 |  |  |  |  | Week-5 |  |  |  |  | Week-6 |  |  |  |  | Week-7 |  |  |  |  | Week-8 |  |  |  |  | Week-9 |  |  |  |  | Week-10 |  |  |  |  | Week-11 |  |  |  |  | Week-12 | [5 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15
[7 empty] | 2025-01-19 | 2025-01-20 | 2025-01-21 | 2025-01-22 | 2025-01-23 | 2025-02-07 | 2025-01-24 | 2025-01-25 | 2025-01-26 | 2025-01-27 | 2025-01-28 | 2025-01-29 | 2025-01-30 | 2025-01-31 | 2025-02-01 | 2025-02-02 | 2025-02-03 | 2025-02-04 | 2025-02-05 | 2025-02-06 | 2025-02-07 | 2025-02-08 | 2025-02-09 | 2025-02-10 | 2025-02-11 | 2025-02-12 | 2025-02-13 | 2025-02-14 | 2025-02-15 | 2025-02-16 | 2025-02-17 | 2025-02-18 | 2025-02-19 | 2025-02-20 | 2025-02-21 | 2025-02-22 | 2025-02-23 | 2025-02-24 | 2025-02-25 | 2025-02-26 | 2025-02-27 | 2025-02-28 | 2025-03-01 | 2025-03-02 | 2025-03-03 | 2025-03-04 | 2025-03-05 | 2025-03-06 | 2025-03-07 | 2025-03-08 | 2025-03-09 | 2025-03-10 | 2025-03-11 | 2025-03-12 | 2025-03-13 | 2025-03-14 | 2025-03-15 | 2025-03-16 | 2025-03-17 | 2025-03-18 | 2025-03-19 | 2025-03-20 | 2025-03-21 | 2025-03-22 | 2025-03-23 | 2025-03-24 | 2025-03-25 | 2025-03-26 | 2025-03-27 | 2025-03-28 | 2025-03-29 | 2025-03-30 | 2025-03-31 | 2025-04-01 | 2025-04-02 | 2025-04-03 | 2025-04-04 | 2025-04-05 | 2025-04-06 | 2025-04-07 | 2025-04-08 | 2025-04-09 | 2025-04-10 | 2025-04-11 | 2025-04-12 | 2025-04-13 | 2025-04-14 | 2025-04-15 | 2025-04-16 | 2025-04-17 | 2025-04-18 | 2025-04-19 | 2025-04-20 | 2025-04-21 | 2025-04-22 | 2025-04-23 | 2025-04-24 | 2025-04-25 | 2025-04-26 | 2025-04-27 | 2025-05-13 | 2025-04-28 | 2025-04-29 | 2025-04-30
Task ID | Task/Activity | Start Date | End Date | Key Player | Days | Progress
A | Project Brief | 2023-10-06 | 2023-10-06 |  | 1 | 0%
1 | Research on MMC (Modern Methods of Construction) of Dome Structures | 2025-01-19 | 2023-01-26 |  | 18 | 0%
1.1 | Conduct a comprehensive literature review | 2023-01-19 | 2023-01-25 |  | 7 | 0%
1.2 | Perform benchmarking and case study analysis | 2023-01-21 | 2023-01-25 |  | 5 | 0%
1.3 | Material and structural evaluation | 2023-01-26 | 2023-01-26 |  | 1 | 0%
2 | Research on Sustainability and Net Zero Carbon | 2023-02-06 | 2023-03-12 |  | 35 | 0% | [6 empty] | `
2.1 | Review sustainability standards and best practices | 2023-02-08 | 2023-02-14 |  | 7 | 0%
2.2 | Conduct an environmental impact and material assessment | 2023-02-15 | 2023-02-18 |  | 4 | 0%
2.3 | Develop an energy and waste management strategy | 2023-02-19 | 2023-02-24 |  | 6 | 0%
3 | Design a 3D Model Integrating Dome of Vision and Hanging Gardens of Babylon Concepts | 2023-02-27 | 2023-03-19 |  | 21 | 0%
3.1 | Ideation and conceptual sketching | 2023-03-03 | 2023-03-12 |  | 9 | 0%
3.2 | Develop and refine 3D model | 2023-03-04 | 2023-03-12 |  | 9 | 0%
4 | Integrate Net-Zero Carbon and Sustainability Goals into the Design | 2023-03-08 | 2023-03-19 |  | 12 | 0%
4.1 | Integrate Renewable Energy Solutions | 2023-03-08 | 2023-03-12 |  | 4 | 0%
4.2 | Implement passive design strategies | 2023-03-09 | 2023-03-13 |  | 4 | 0%
4.3 | Ensure compliance with LEED and BREEAM | 2023-03-14 | 2023-03-17 |  | 3 | 0%
5 | Integrate Modular and Offsite Design Solutions | 2023-03-15 | 2023-04-30 |  | 25 | 0%
5.1 | Research prefabrication and modular construction techniques | 2023-03-15 | 2023-03-19 |  | 5 | 0%
5.2 | Develop assembly plan | 2023-03-20 | 2023-03-24 |  | 5 | 0%
5.3 | Conduct risk assessment and establish contingency plans | 2023-04-17 | 2023-04-20 |  | 4 | 0%

## Project Closure Schedule
West End Community Sensory Garden
Build Planet Zero #2
KEYS
Completed
Not completed
Overdue tasks
|  |  |  | Delayed Completion | [5 empty] | Week 14 | [6 empty] | Week 15
 | time axis 2025-03-24 to 2025-05-09
Task ID | Task/Activity | Start Date | End Date | Key Player | Days | Progress
3 | Project Closure | 2025-03-26 | 2025-04-27 |  | 33 | 21.21% | bar: 2025-03-26 to 2025-05-09
3.1 | Prepare for project Closure | 2025-03-26 | 2025-04-23 |  | 29 | 24.14% | bar: 2025-03-26 to 2025-04-23
3.1.2 | Create Project Closure plan | 2025-03-26 | 2025-03-27 | Kufre | 2 | 100% | bar: 2025-03-26 to 2025-03-27
3.1.3 | Mindmap client brief to deliverables | 2025-03-27 | 2025-03-28 | Kufre | 2 | 100% | bar: 2025-03-26 to 2025-03-27
3.1.1 | Structure Final project report including heading and subheading and share with team for feedback | 2025-03-27 | 2025-04-04 | Shebi | 9 | 100% | bar: 2025-03-27 to 2025-04-04
3.1.4 | Develop the report concurrently through the design phase | 2025-04-07 | 2025-04-23 | Shebi | 17 | 64.71% | bar: 2025-03-26 to 2025-04-23
3.2 | BIM design phase 1 | 2025-03-26 | 2025-04-01 | Jayaprekesh | 7 | 100% | bar: 2025-03-26 to 2025-04-01
3.2.1 | Create spatial design of the layout | 2025-03-26 | 2025-03-28 | Jayaprekesh | 3 | 100% | bar: 2025-03-26 to 2025-03-28
3.2.2 | Situate all structures within layout | 2025-03-26 | 2025-03-28 | Jayaprekesh | 3 | 100% | bar: 2025-03-26 to 2025-03-28
3.2.3 | Integrate rainwater harvesting and sustainable water management solutions into the design. | 2025-03-26 | 2025-03-28 | Jayaprekesh | 3 | 100% | bar: 2025-03-26 to 2025-03-28
3.2.4 | Create 2D and 3D sketch of final design option | 2025-03-28 | 2025-04-01 | Jayaprekesh | 5 | 100% | bar: 2025-03-28 to 2025-04-01
3.2.5 | Share with project team for feedback | 2025-04-01 | 2025-04-01 | Jayaprekesh | 1 | 100% | bar: 2025-04-01
4 | BIM Design phase 2 | 2025-04-01 | 2025-04-04 |  | 4 | 100% | bar: 2025-04-01 to 2025-04-02; 2025-04-14 to 2025-04-15
4.1 | Preliminary Design | 2025-04-01 | 2025-04-04 |  | 4 | 100% | bar: 2025-04-01 to 2025-04-02; 2025-04-14 to 2025-04-15
4.1.1 | Develop reviewed sketch to LOD 200 for conceptualization of renewable energy integration and modularizattion | 2025-04-01 | 2025-04-02 | Jayaprekesh | 2 | 100% | bar: 2025-04-01 to 2025-04-02
4.1.2 | Research on BIM based DfMA of design | 2025-04-01 | 2025-04-02 | Kufre | 2 | 100% | bar: 2025-04-01 to 2025-04-02
4.1.3 | Research and report on suitable renewable energy for integration | 2025-04-01 | 2025-04-02 | Shebi | 2 | 100% | bar: 2025-04-01 to 2025-04-02
4.1.4 | Identify optimal locations within the design for solar panels and other renewable systems. | 2025-04-02 | 2025-04-02 | Jayaprekesh | 1 | 100% | bar: 2025-04-02
4.1.7 | Simulate the impact of passive strategies on overall energy consumption. | 2025-04-03 | 2025-04-04 | Jayaprekesh | 2 | 0% | bar: 2025-04-14 to 2025-04-15
4.1.8 | Develop integrated report of DfMA and renewable energy integration into Preliminary Design | 2025-04-03 | 2025-04-04 | Kufre | 2 | 0% | bar: 2025-04-14 to 2025-04-15
4.1.9 | Share with project team for feedback | 2025-03-04 | 2025-04-04 | Kufre | 32 | 0% | bar: 2025-04-15
4.2 | BIM design phase 3 | 2025-04-07 | 2025-04-18 |  | 12 | 91.67% | bar: 2025-04-07 to 2025-04-17
4.2.1 | Develop detailed 3D design of structure at LOD 300 incoperating renewable energy and DfMA solutions | 2025-04-07 | 2025-04-11 | Jayaprekesh | 5 | 100% | bar: 2025-04-07 to 2025-04-11
4.2.2 | Third Industrial Supervision | 2025-04-08 | 2025-04-11 | Team | 4 | bar: 2025-04-08
4.2.3 | Extract detailed material schedule for verification of embodied carbon goals and estimation | 2025-04-14 | 2025-04-15 | Jayaprekesh | 2 | 0% | bar: 2025-04-14 to 2025-04-15
4.2.4 | Prepare material selecction report for final report | 2025-04-16 | 2025-04-17 | Collins | 2 | 0% | bar: 2025-04-14 to 2025-04-15
4.2.5 | Reseach potential suppliers and their loaction for embodied carbon goals | 2025-04-16 | 2025-04-17 | Collins | 2 | 0% | bar: 2025-04-16 to 2025-04-17
4.2.6 | Prepare report on potential supplier stakeholders for final report | 2025-04-16 | 2025-04-17 | Collins | 2 | 0% | bar: 2025-04-16 to 2025-04-17
4.2.7 | Create 3D rendered model in Lumion/Twinmotion. | 2025-04-17 | 2025-04-18 | Jayaprekesh | 2 | bar: 2025-04-17 to 2025-04-18
4.3 | Ensure Certification and Compliance | 2025-04-18 | 2025-04-21 |  | 4 | 0% | bar: 2025-04-18 to 2025-04-21
4.3.1 | Mind Map design elements to the requirements of Passivhaus certification | 2025-04-18 | 2025-04-21 | Jayaprekesh | 4 | 0% | bar: 2025-04-18 to 2025-04-21
4.3.2 | Mind Map design elements to the requirements of client brief | 2025-04-18 | 2025-04-21 | Collins | 4 | 0% | bar: 2025-04-18 to 2025-04-21
4.3.3 | Identify any gaps or areas for improvement. | 2025-04-18 | 2025-04-21 | Collins | 4 | 0% | bar: 2025-04-18 to 2025-04-21
4.3.4 | Prepare a Passivhause compliance report as a section for Project Report | 2025-04-18 | 2025-04-21 | Jayaprekesh | 4 | 0% | bar: 2025-04-18 to 2025-04-21
4.3.5 | Create a draft closeout presentation | 2025-04-18 | 2025-04-21 | Team | 4 | bar: 2025-04-18 to 2025-04-21
5 | Document preperation and submission | 2025-04-22 | 2025-04-24 |  | 3 | 0% | bar: 2025-04-22 to 2025-04-24
5.1 | Construction Risk Assesment and Mitigation | 2025-04-22 | 2025-04-23 |  | 2 | 0% | bar: 2025-04-22 to 2025-04-23
5.1.1 | Identify risks associated with delivery of design | 2025-04-22 | 2025-04-23 | Kufre | 2 | 0% | bar: 2025-04-22 to 2025-04-23
5.1.2 | Develop mitigation strategies and document contingency plans. | 2025-04-22 | 2025-04-23 | Kufre | 2 | 0% | bar: 2025-04-22 to 2025-04-23
5.1.3 | Update tproject report to include Risk and Mitigation | 2025-04-22 | 2025-04-23 | Shebi | 2 | 0% | bar: 2025-04-22 to 2025-04-23
5.1.5 | Coming in to land support | 2025-04-22 | 2025-04-24 | Team | 3 | bar: 2025-04-22 to 2025-04-24
5.1.4 | VR walkthrough and high-quality rendered images of final model | 2025-04-23 | 2025-04-23 | Jayaprekesh | 1 | bar: 2025-04-23
5.2 | Final Project Presentation | 2025-04-23 | 2025-04-26 |  | 4 | 0% | bar: 2025-04-23 to 2025-04-26
5.2.1 | Collect and integrated project infographics required | 2025-04-23 | 2025-04-24 | Shebi | 2 | 0% | bar: 2025-04-23 to 2025-04-24
5.2.2 | Share with project team for feedback | 2025-04-25 | 2025-04-25 | Shebi | 1 | 0% | bar: 2025-04-25
5.2.3 | Final professional training session | 2025-04-25 | 2025-04-25 | Team | 1 | bar: 2025-04-25
5.2.4 | Update and submit based on feedback | 2025-04-26 | 2025-04-26 | Shebi | 1 | 0% | bar: 2025-04-26
5.3 | Project Report | 2025-04-22 | 2025-04-26 |  | 5 | 0% | bar: 2025-04-22 to 2025-05-09
5.3.1 | Complete project report | 2025-04-23 | 2025-04-24 | Kufre | 2 | 0% | bar: 2025-04-23 to 2025-04-24
5.3.2 | Share with project team for feedback | 2025-04-25 | 2025-04-25 | Kufre | 1 | 0% | bar: 2025-04-25
5.3.3 | Update report based on feedback | 2025-04-26 | 2025-04-26 | Kufre | 1 | 0% | bar: 2025-04-26
5.3.4 | Client Close-Out meetings | 2025-04-28 | 2025-04-28 | Team | 1 | 0% | bar: 2025-04-28
5.3.5 | End of Project Celebration | 2025-05-09 | 2025-05-09 | Team | 1 | 0% | bar: 2025-05-09
Formulas:
Start Date = [Start Date, row below]

## 04.02.2025 v1.0
West End Community Sensory Garden
Build Planet Zero #2
KEYS
Completed
Not completed
Overdue tasks
|  |  |  | Delayed Completion |  |  | z | Week-1 |  |  |  |  | Week-2 |  |  |  | Week-3 |  |  |  |  | Week-4 |  |  |  |  | Week-5 |  |  |  |  | Week-6 |  |  |  |  | Week-7 |  |  |  |  | Week-8 |  |  |  |  | Week-9 |  |  |  |  | Week-10 |  |  |  |  | Week-11 |  |  |  |  | Week-12 | [5 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15
[7 empty] | 2025-01-19 | 2025-01-20 | 2025-01-21 | 2025-01-22 | 2025-01-23 | 2025-02-07 | 2025-01-24 | 2025-01-25 | 2025-01-26 | 2025-01-27 | 2025-01-28 | 2025-01-29 | 2025-01-30 | 2025-01-31 | 2025-02-01 | 2025-02-02 | 2025-02-03 | 2025-02-04 | 2025-02-05 | 2025-02-06 | 2025-02-07 | 2025-02-08 | 2025-02-09 | 2025-02-10 | 2025-02-11 | 2025-02-12 | 2025-02-13 | 2025-02-14 | 2025-02-15 | 2025-02-16 | 2025-02-17 | 2025-02-18 | 2025-02-19 | 2025-02-20 | 2025-02-21 | 2025-02-22 | 2025-02-23 | 2025-02-24 | 2025-02-25 | 2025-02-26 | 2025-02-27 | 2025-02-28 | 2025-03-01 | 2025-03-02 | 2025-03-03 | 2025-03-04 | 2025-03-05 | 2025-03-06 | 2025-03-07 | 2025-03-08 | 2025-03-09 | 2025-03-10 | 2025-03-11 | 2025-03-12 | 2025-03-13 | 2025-03-14 | 2025-03-15 | 2025-03-16 | 2025-03-17 | 2025-03-18 | 2025-03-19 | 2025-03-20 | 2025-03-21 | 2025-03-22 | 2025-03-23 | 2025-03-24 | 2025-03-25 | 2025-03-26 | 2025-03-27 | 2025-03-28 | 2025-03-29 | 2025-03-30 | 2025-03-31 | 2025-04-01 | 2025-04-02 | 2025-04-03 | 2025-04-04 | 2025-04-05 | 2025-04-06 | 2025-04-07 | 2025-04-08 | 2025-04-09 | 2025-04-10 | 2025-04-11 | 2025-04-12 | 2025-04-13 | 2025-04-14 | 2025-04-15 | 2025-04-16 | 2025-04-17 | 2025-04-18 | 2025-04-19 | 2025-04-20 | 2025-04-21 | 2025-04-22 | 2025-04-23 | 2025-04-24 | 2025-04-25 | 2025-04-26 | 2025-04-27 | 2025-05-13 | 2025-04-28 | 2025-04-29 | 2025-04-30
Task ID | Task/Activity | Start Date | End Date | Key Player | Days | Progress
A | Project Brief | 2023-10-06 | 2023-10-06 |  | 1 | 100%
1 | Research on MMC (Modern Methods of Construction) of Dome Structures | 2025-01-19 | 2023-01-26 |  | 18 | 100%
1.1 | Conduct a comprehensive literature review | 2023-01-19 | 2023-01-25 |  | 7 | 100%
1.2 | Perform benchmarking and case study analysis | 2023-01-21 | 2023-01-25 |  | 5 | 100%
1.3 | Material and structural evaluation | 2023-01-26 | 2023-01-26 |  | 1 | 0%
2 | Research on Sustainability and Net Zero Carbon | 2023-02-06 | 2023-03-12 |  | 35 | 100% | [6 empty] | `
2.1 | Review sustainability standards and best practices | 2023-02-08 | 2023-02-14 |  | 7 | 100%
2.2 | Conduct an environmental impact and material assessment | 2023-02-15 | 2023-02-18 |  | 4 | 100%
2.3 | Develop an energy and waste management strategy | 2023-02-19 | 2023-02-24 |  | 6 | 20%
3 | Design a 3D Model Integrating Dome of Vision and Hanging Gardens of Babylon Concepts | 2023-02-27 | 2023-03-19 |  | 21 | 10%
3.1 | Ideation and conceptual sketching | 2023-03-03 | 2023-03-12 |  | 9 | 0%
3.2 | Develop and refine 3D model | 2023-03-04 | 2023-03-12 |  | 9 | 0%
4 | Integrate Net-Zero Carbon and Sustainability Goals into the Design | 2023-03-08 | 2023-03-19 |  | 12 | 0%
4.1 | Integrate Renewable Energy Solutions | 2023-03-08 | 2023-03-12 |  | 4 | 0%
4.2 | Implement passive design strategies | 2023-03-09 | 2023-03-13 |  | 4 | 0%
4.3 | Ensure compliance with LEED and BREEAM | 2023-03-14 | 2023-03-17 |  | 3 | 0%
5 | Integrate Modular and Offsite Design Solutions | 2023-03-15 | 2023-04-30 |  | 25 | 0%
5.1 | Research prefabrication and modular construction techniques | 2023-03-15 | 2023-03-19 |  | 5 | 0%
5.2 | Develop assembly plan | 2023-03-20 | 2023-03-24 |  | 5 | 0%
5.3 | Conduct risk assessment and establish contingency plans | 2023-04-17 | 2023-04-20 |  | 4 | 0%

## To-Do (2)
OBJ NO. | Objective Description | Task Number | Task Description | Start | end | Responsible | Progress
1 | Research on MMC (Modern Methods of Construction) of Dome Structures
1.1 | Conduct a Comprehensive Literature Review |  | Identify and list key academic journals, industry publications, and reports on MMC and dome construction.
Gather relevant case studies and technical documents.
Summarize findings in a mini report that outlines best practices, innovations, and challenges. This is a section of our final consultancy report.
1.2 | Perform Benchmarking and Case Study Analysis |  | Select at least three successful dome projects that have used MMC.
Analyze project documentation, performance metrics, and cost-benefit analyses.
Interview or consult experts (if feasible) to validate findings.
Prepare a comparative analysis document highlighting key lessons learned.
1.3 | Material and Structural Evaluation |  | Compile a list of sustainable materials suitable for dome construction.
Request technical data and sample analyses from suppliers.
Conduct or review structural simulations focusing on load-bearing capacity and durability.
Document the pros and cons of each material option in relation to sustainability and cost.
2 | Research on Sustainability and Net Zero Carbon
2.1 | Review Sustainability Standards and Best Practices |  | Identify and review standards such as LEED, BREEAM, and other green building certifications.
Gather data on sustainable construction methods and renewable energy integrations.
2.2 | Conduct an Environmental Impact and Material Assessment |  | Create a sustainability checklist tailored to the project’s scope.
Develop a matrix comparing low-carbon, recycled, and locally sourced material options.
Perform an environmental impact assessment (EIA) for each material.
2.3 | Develop an Energy and Waste Management Strategy |  | Recommend material choices based on sustainability, performance, and cost criteria.
Identify potential renewable energy systems (solar, wind, rainwater harvesting).
Map out energy efficiency and passive design strategies.
Draft a waste management and reduction plan.
Integrate these strategies into a comprehensive sustainability guideline document.
3 | Design a 3D Model Integrating Dome of Vision and Hanging Gardens of Babylon Concepts
3.1 | Ideation and Conceptual Sketching |  | Organize a creative brainstorming session with key stakeholders.
Develop initial hand sketches or digital mock-ups that combine both design inspirations.
Validate early concepts against project requirements and sustainability criteria.
3.2 | Software Selection and 3D Modeling Setup |  | Evaluate and select 3D modeling software (e.g., Revit, Rhino, SketchUp).
Install and configure the chosen software with necessary plugins and libraries.
Provide a brief training session or tutorial for team members on the chosen platform.
3.3 | Develop and Refine the 3D Model |  | Build an initial 3D model integrating the dome structure with garden elements.
Simulate environmental factors (light, ventilation, and energy flows) in the design.
Present the model to stakeholders and gather structured feedback.
4.1 | Incorporate revisions and finalize the 3D model for further development. |  | Identify optimal locations within the design for solar panels and other renewable systems.
Model energy output and efficiency impacts.
Validate renewable energy integration against the sustainability checklist.
4.2 | Implement Passive Design Strategies |  | Research passive heating, cooling, and ventilation strategies.
Integrate rainwater harvesting and sustainable water management solutions into the design.
Simulate the impact of passive strategies on overall energy consumption.
4.3 | Ensure Certification and Compliance |  | Map design elements to the requirements of green building certifications (e.g., LEED, BREEAM).
Identify any gaps or areas for improvement.
Prepare a compliance report and action plan to address certification criteria.
5 | Integrate Modular and Offsite Design Solutions
5.1 | Research Prefabrication and Modular Construction Techniques |  | Investigate current trends and best practices in prefabrication.
Identify and shortlist suppliers and manufacturers experienced in modular construction.
Review case studies on modular building projects to extract lessons and best practices.
5.2 | Develop a Detailed Modular Design and Assembly Plan |  | Break down the design into modular components.
Create detailed assembly and installation plans including logistics, transport, and on-site integration.
Collaborate with potential suppliers to verify design feasibility and cost implications.
5.3 | Conduct Risk Assessment and Establish Contingency Plans |  | Identify risks associated with modular and offsite construction (e.g., transportation delays, assembly issues).
Develop mitigation strategies and document contingency plans.
Update the master schedule to reflect risk management measures and review timelines.

## To-Do
OBJ NO. | Objective Description | Purpose | Task Number | Task Description | To-Do List | R | A | C | I | STATUS
1 | Research on MMC (Modern Methods of Construction) of Dome Structures | Establish a robust knowledge base and best practice framework for using MMC in dome construction. | 1.1 | Conduct a Comprehensive Literature Review | Identify and list key academic journals, industry publications, and reports on MMC and dome construction.
Gather relevant case studies and technical documents.
Summarize findings in a mini report that outlines best practices, innovations, and challenges. This is a section of our final consultancy report.
|  |  | 1.2 | Perform Benchmarking and Case Study Analysis | Select at least three successful dome projects that have used MMC.
Analyze project documentation, performance metrics, and cost-benefit analyses.
Interview or consult experts (if feasible) to validate findings.
Prepare a comparative analysis document highlighting key lessons learned.
|  |  | 1.3 | Material and Structural Evaluation | Compile a list of sustainable materials suitable for dome construction.
Request technical data and sample analyses from suppliers.
Conduct or review structural simulations focusing on load-bearing capacity and durability.
Document the pros and cons of each material option in relation to sustainability and cost.
2 | Research on Sustainability and Net Zero Carbon | Ensure the project integrates sustainable practices and meets net-zero carbon targets. | 2.1 | Review Sustainability Standards and Best Practices | Identify and review standards such as LEED, BREEAM, and other green building certifications.
Gather data on sustainable construction methods and renewable energy integrations.
Create a sustainability checklist tailored to the project’s scope.
|  |  | 2.2 | Conduct an Environmental Impact and Material Assessment | Develop a matrix comparing low-carbon, recycled, and locally sourced material options.
Perform an environmental impact assessment (EIA) for each material.
Recommend material choices based on sustainability, performance, and cost criteria.
|  |  | 2.3 | Develop an Energy and Waste Management Strategy | Identify potential renewable energy systems (solar, wind, rainwater harvesting).
Map out energy efficiency and passive design strategies.
Draft a waste management and reduction plan.
Integrate these strategies into a comprehensive sustainability guideline document.
3 | Design a 3D Model Integrating Dome of Vision and Hanging Gardens of Babylon Concepts | Create a digital design that embodies the visionary elements of the Dome of Vision and the Hanging Gardens while adhering to sustainability principles. | 3.1 | Ideation and Conceptual Sketching | Organize a creative brainstorming session with key stakeholders.
Develop initial hand sketches or digital mock-ups that combine both design inspirations.
Validate early concepts against project requirements and sustainability criteria.
|  |  | 3.2 | Software Selection and 3D Modeling Setup | Evaluate and select 3D modeling software (e.g., Revit, Rhino, SketchUp).
Install and configure the chosen software with necessary plugins and libraries.
Provide a brief training session or tutorial for team members on the chosen platform.
|  |  | 3.3 | Develop and Refine the 3D Model | Build an initial 3D model integrating the dome structure with garden elements.
Simulate environmental factors (light, ventilation, and energy flows) in the design.
Present the model to stakeholders and gather structured feedback.
Incorporate revisions and finalize the 3D model for further development.
4 | Integrate Net-Zero Carbon and Sustainability Goals into the Design | Ensure that all design elements support net-zero carbon ambitions and sustainability. | 4.1 | Integrate Renewable Energy Solutions | Identify optimal locations within the design for solar panels and other renewable systems.
Model energy output and efficiency impacts.
Validate renewable energy integration against the sustainability checklist.
|  |  | 4.2 | Implement Passive Design Strategies | Research passive heating, cooling, and ventilation strategies.
Integrate rainwater harvesting and sustainable water management solutions into the design.
Simulate the impact of passive strategies on overall energy consumption.
|  |  | 4.3 | Ensure Certification and Compliance | Map design elements to the requirements of green building certifications (e.g., LEED, BREEAM).
Identify any gaps or areas for improvement.
Prepare a compliance report and action plan to address certification criteria.
5 | Integrate Modular and Offsite Design Solutions | Enhance construction efficiency and flexibility through modular and offsite design strategies. | 5.1 | Research Prefabrication and Modular Construction Techniques | Investigate current trends and best practices in prefabrication.
Identify and shortlist suppliers and manufacturers experienced in modular construction.
Review case studies on modular building projects to extract lessons and best practices.
|  |  | 5.2 | Develop a Detailed Modular Design and Assembly Plan | Break down the design into modular components.
Create detailed assembly and installation plans including logistics, transport, and on-site integration.
Collaborate with potential suppliers to verify design feasibility and cost implications.
|  |  | 5.3 | Conduct Risk Assessment and Establish Contingency Plans | Identify risks associated with modular and offsite construction (e.g., transportation delays, assembly issues).
Develop mitigation strategies and document contingency plans.
Update the master schedule to reflect risk management measures and review timelines.

## Gantt Chart Rework
West End Community Sensory Garden
Build Planet Zero #2
KEYS
Completed
Not completed
Overdue tasks
[8 empty] | Week-1 |  |  |  |  | Week-2 | [6 empty] | Week-3 | [6 empty] | Week-4 | [6 empty] | Week-5 | [6 empty] | Week-6 | [6 empty] | Week -8 | [6 empty] | Week-8 | [6 empty] | Week-9 | [6 empty] | Week-10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week - 14
Task | Task/Activity | Start Date | End Date | Key Players | Days | Progress | 2025-01-19 | 2025-01-20 | 2025-01-21 | 2025-01-22 | 2025-01-23 | time axis 2025-01-24 to 2025-04-23
1 | Research on MMC (Modern Methods of Construction) of Dome Structures | 2025-01-19 | 2025-02-09 |  | 22 | 0% | bar: 2025-01-24 to 2025-02-09
1.1 | Conduct a Comprehensive Literature Review | 2025-01-19 | 2023-01-26 |  | 8 | 0% | bar: 2025-01-24 to 2025-01-26
| Identify and list key academic journals, industry publications, and reports on MMC and dome construction. | 2023-01-19 | 2023-01-21 |  | 3 | 0%
| Gather relevant case studies and technical documents. | 2023-01-22 | 2023-01-23 |  | 2 | 0%
| Summarize findings in a mini report that outlines best practices, innovations, and challenges. This is a section of our final consultancy report. | 2023-01-24 | 2023-01-26 |  | 3 | 0% | bar: 2025-01-24 to 2025-01-26
1.2 | Perform Benchmarking and Case Study Analysis | 2023-01-27 | 2023-02-02 |  | 7 | 0% | bar: 2025-01-27 to 2025-02-02
| Select at least three successful dome projects that have used MMC. | 2023-01-27 | 2023-01-28 |  | 2 | 0% | bar: 2025-01-27 to 2025-01-28
| Analyze project documentation, performance metrics, and cost-benefit analyses. | 2023-01-29 | 2023-01-30 |  | 2 | 0% | bar: 2025-01-29 to 2025-01-30
| Interview or consult experts (if feasible) to validate findings. | 2023-01-31 | 2023-01-31 |  | 1 | 0% | bar: 2025-01-31
| Prepare a comparative analysis document highlighting key lessons learned. | 2023-02-01 | 2023-02-02 |  | 2 | 0% | bar: 2025-02-01 to 2025-02-02
1.3 | Material and Structural Evaluation | 2023-02-03 | 2023-02-09 |  | 7 | 0% | bar: 2025-02-03 to 2025-02-09
| Compile a list of sustainable materials suitable for dome construction. | 2023-02-03 | 2023-02-04 |  | 2 | 0% | bar: 2025-02-03 to 2025-02-04
| Request technical data and sample analyses from suppliers. | 2023-02-05 | 2023-02-05 |  | 1 | 0% | bar: 2025-02-05
| Conduct or review structural simulations focusing on load-bearing capacity and durability. | 2023-02-06 | 2023-02-07 |  | 2 | 0% | bar: 2025-02-06 to 2025-02-07
| Document the pros and cons of each material option in relation to sustainability and cost. | 2023-02-08 | 2023-02-09 |  | 2 | 0% | bar: 2025-02-08 to 2025-02-09
2 | Research on Sustainability and Net Zero Carbon | 2023-02-10 | 2023-02-28 |  | 19 | 0% | bar: 2025-02-10 to 2025-02-28
2.1 | Review Sustainability Standards and Best Practices | 2023-02-10 | 2023-02-16 |  | 7 | 0% | bar: 2025-02-10 to 2025-02-18
| Identify and review standards such as LEED, BREEAM, and other green building certifications. | 2023-02-10 | 2023-02-12 |  | 3 | 0% | bar: 2025-02-10 to 2025-02-12
| Gather data on sustainable construction methods and renewable energy integrations. | 2023-02-13 | 2023-02-16 |  | 4 | 0% | bar: 2025-02-13 to 2025-02-16
2.2 | Conduct an Environmental Impact and Material Assessment | 2023-02-17 | 1900-02-22 |  | 7 | 0% | bar: 2025-02-17 to 2025-02-23
| Create a sustainability checklist tailored to the project’s scope. | 2025-02-17 | 2025-02-18 |  | 2 | 0% | bar: 2025-02-17 to 2025-02-18
| Develop a matrix comparing low-carbon, recycled, and locally sourced material options. | 2025-02-19 | 2025-02-20 |  | 2 | 0% | bar: 2025-02-19 to 2025-02-20
| Perform an environmental impact assessment (EIA) for each material. | 2025-02-21 | 2025-02-23 |  | 3 | 0% | bar: 2025-02-21 to 2025-02-23
2.3 | Develop an Energy and Waste Management Strategy | 2025-02-24 | 2025-02-28 |  | 5 | 0% | bar: 2025-02-24 to 2025-02-28
| Recommend material choices based on sustainability, performance, and cost criteria. | 2025-02-24 | 2025-02-25 |  | 2 | bar: 2025-02-24 to 2025-02-25
| Identify potential renewable energy systems (solar, wind, rainwater harvesting). | 2025-03-26 | 2025-02-26 |  | 1 | 0% | bar: 2025-02-26
| Map out energy efficiency and passive design strategies. | 2025-02-27 | 2025-02-27 |  | 1 | 0% | bar: 2025-02-27
| Draft a waste management and reduction plan. | 2025-02-28 | 2025-02-28 |  | 1 | 0% | bar: 2025-02-28
| Integrate these strategies into a comprehensive sustainability guideline document. | 2025-02-28 | 2025-02-28 |  | 1 | 0% | bar: 2025-02-28
3 | Design a 3D Model Integrating Dome of Vision and Hanging Gardens of Babylon Concepts | 2025-03-01 | 2025-03-22 |  | 22 | 0% | bar: 2025-03-01 to 2025-03-22
3.1 | Ideation and Conceptual Sketching | 2025-03-01 | 2025-03-05 |  | 5 | 0% | bar: 2025-03-01 to 2025-03-05
| Organize a creative brainstorming session with key stakeholders. | 2025-03-01 | 2025-03-02 |  | 2 | 0% | bar: 2025-03-01 to 2025-03-02
| Develop initial hand sketches or digital mock-ups that combine both design inspirations. | 2025-03-03 | 2025-03-04 |  | 2 | 0% | bar: 2025-03-03 to 2025-03-04
| Validate early concepts against project requirements and sustainability criteria. | 2025-03-05 | 2025-03-05 |  | 1 | 0% | bar: 2025-03-05
3.2 | Software Selection and 3D Modeling Setup | 2025-03-06 | 2025-03-09 |  | 4 | 0% | bar: 2025-03-06 to 2025-03-09
| Evaluate and select 3D modeling software (e.g., Revit, Rhino, SketchUp). | 2025-03-06 | 2025-03-06 |  | 1 | 0% | bar: 2025-03-06
| Install and configure the chosen software with necessary plugins and libraries. | 2025-03-07 | 2025-03-07 |  | 1 | 0% | bar: 2025-03-07
| Provide a brief training session or tutorial for team members on the chosen platform. | 2025-03-08 | 2025-03-09 |  | 2 | 0% | bar: 2025-03-07 to 2025-03-09
3.3 | Develop and Refine the 3D Model | 2025-03-10 | 2025-03-22 |  | 12 | 0% | bar: 2025-03-10 to 2025-03-22
| Build an initial 3D model integrating the dome structure with garden elements. | 2025-03-10 | 2025-03-15 |  | 6 | 0% | bar: 2025-03-10 to 2025-03-15
| Simulate environmental factors (light, ventilation, and energy flows) in the design. | 2025-03-16 | 2025-03-18 |  | 3 | 0% | bar: 2025-03-16 to 2025-03-18
| Present the model to stakeholders and gather structured feedback. | 2025-03-19 | 2025-03-22 |  | 4 | 0% | bar: 2025-03-19 to 2025-03-22
4 | Integrate Net-Zero Carbon and Sustainability Goals into the Design | 2025-03-23 | 2025-04-05 |  | 14 | 0% | bar: 2025-03-23 to 2025-04-05
4.1 | Incorporate revisions and finalize the 3D model for further development. | 2025-03-23 | 2025-03-26 |  | 4 | 0% | bar: 2025-03-23 to 2025-03-26
| Identify optimal locations within the design for solar panels and other renewable systems. | 2025-03-23 | 2025-03-24 |  | 2 | 0% | bar: 2025-03-23 to 2025-03-24
| Model energy output and efficiency impacts. | 2025-03-23 | 2025-03-24 |  | 2 | 0% | bar: 2025-03-25 to 2025-03-26
| Validate renewable energy integration against the sustainability checklist. | 2025-03-25 | 2025-03-26 |  | 2 | 0% | bar: 2025-03-27 to 2025-03-28
4.2 | Implement Passive Design Strategies | 2025-03-27 | 2025-04-01 |  | 6 | 0% | bar: 2025-03-29 to 2025-04-03
| Research passive heating, cooling, and ventilation strategies. | 2025-03-27 | 2025-03-28 |  | 2 | 0%
| Integrate rainwater harvesting and sustainable water management solutions into the design. | 2025-03-29 | 2025-03-30 |  | 2 | 0%
| Simulate the impact of passive strategies on overall energy consumption. | 2025-03-31 | 2025-04-01 |  | 2 | 0%
4.3 | Ensure Certification and Compliance | 2025-04-02 | 2025-04-05 |  | 4 | 0%
| Map design elements to the requirements of green building certifications (e.g., LEED, BREEAM). | 2025-04-02 | 2025-04-03 |  | 2 | 0%
| Identify any gaps or areas for improvement. | 2025-04-02 | 2025-04-03 |  | 2 | 0%
| Prepare a compliance report and action plan to address certification criteria. | 2025-04-04 | 2025-04-05 |  | 2 | 0%
5 | Integrate Modular and Offsite Design Solutions | 2025-04-06 | 2025-04-30 |  | 25 | 0%
5.1 | Research Prefabrication and Modular Construction Techniques | 2025-04-06 | 2025-04-10 |  | 5 | 0%
| Investigate current trends and best practices in prefabrication. | 2025-04-06 | 2025-04-07 |  | 2 | 0%
| Identify and shortlist suppliers and manufacturers experienced in modular construction. | 2025-04-08 | 2025-04-09 |  | 2 | 0%
| Review case studies on modular building projects to extract lessons and best practices. | 2025-04-10 | 2025-04-10 |  | 1 | 0%
5.2 | Develop a Detailed Modular Design and Assembly Plan | 2025-04-11 | 2025-04-19 |  | 9 | 0%
| Break down the design into modular components. | 2025-04-11 | 2025-04-13 |  | 3 | 0%
| Create detailed assembly and installation plans including logistics, transport, and on-site integration. | 2025-04-14 | 2025-04-16 |  | 3 | 0%
| Collaborate with potential suppliers to verify design feasibility and cost implications. | 2025-04-17 | 2025-04-19 |  | 3 | 0%
5.3 | Conduct Risk Assessment and Establish Contingency Plans | 2025-03-20 | 2025-04-30 |  | 11 | 0%
| Identify risks associated with modular and offsite construction (e.g., transportation delays, assembly issues). | 2025-04-20 | 2025-04-23 |  | 4 | 0%
| Develop mitigation strategies and document contingency plans. | 2025-03-24 | 2025-04-26 |  | 3 | 0%
| Update the master schedule to reflect risk management measures and review timelines. | 2025-04-27 | 2025-04-30 |  | 4 | 0%